## Slide 1: Three-State Air Quality Study (3SAQS) Three-State Data Warehouse (3SDW)
3SAQS Pilot Project Modeling Overview
University of North Carolina (UNC-IE)
ENVIRON International Corporation (ENVIRON)
October 10, 2014

## Slide 2: Summary
3SAQS Pilot Project Timeline and Deliverables
Emissions Inventory Improvements
Key Collaborations and Interactions
Modeling Highlights
  WRF Meteorology
  SMOKE Emissions
  CAMx Air Quality
Oil and Gas Inventories
Monitoring Network Analysis
3SDW Support and Tool Development
Status and Next Steps

## Slide 3: 3SAQS Pilot Project Timeline
2012
2013
2014
OCT 2012
Pilot Project Start
JAN 2013
EI Improvement
Meetings With
CO, UT, WY
NOV-DEC 2012
CO, UT, WY
2008 EI Analysis and Evaluation
FEB 2014
3SAQS Monitoring Network Report
OCT 2013
WRF 2011 Sensitivities
AUG 2014
CAMx 2008b, WRF 2011, 2011 Oil & Gas EI,
2011a Emissions
JUL 2014
Final 2008 Emissions
OCT 2014
CAMx 2011a MPE
SEP 2014
SMOKE 2011a
NOV 2014-APR 2015
CAMx 2011 Sensitivities
AUG 2012
CAMx 2008a
JUN 2012
Emissions VOC Reactivity Analysis
FEB-MAY 2012
2008 EI Modeling
MAR-JUN 2014
2011 EI Modeling

## Slide 4: 3SAQS Pilot Project Major Deliverables
Modeling Platforms
  Modeling input/output data, software, and scripts
  2008 version A and B
    SMOKE and CAMx
    Base and Future Year (2020)
  2011 version A
    WRF, SMOKE, and CAMx
    Base and Future Year (2020)
Emissions
  2011 O&G inventory
  Data updates for 3-state sources
  2008, 2011, 2020 inventories
    Fusion of NEI and 3-state inventories
Monitoring Network Assessment

## Slide 5: 3SAQS Pilot Project Major Deliverables
Key Analysis Products
  Inventory comparisons
  VOC reactivity analysis
  Model performance evaluations
    CAMx 2008
    WRF 2011
    CAMx 2011
  Methane inventory analysis
Modeling Sensitivities
  Boundary conditions
  US background air quality
  Ammonia emissions
  Oil and gas emissions
  Winter ozone

## Slide 6: Key Findings: Meteorology
Completed 2011 WRF modeling and evaluation
2008 and 2011 WRF performance acceptable and comparable
WRF configuration based on systematic configuration testing
Episodic performance issues, particularly for winter inversions
Observed
May 2011
Total Precip (in.)
WRF
May 2011
Total Precip (in.)

## Slide 7: Key Findings: Emissions
New 2011 O&G EI
2008 > 2011 > 2020
  Trends vary by state/sector/pollutant
  General decrease in emissions through time
  Exception is VOC from O&G sources

## Slide 8: Key Findings: Emissions
Collaboration with CO, UT, WY state DAQs to obtain data, review emissions, and get feedback on protocols/evaluations
Updates to key sectors/pollutants
  Agricultural NH3 – point CAFO locations used to improve the spatial allocation of livestock emissions
  On-road mobile – link-based VMT from CO used to improve spatial allocation of on-road mobile sources in CO
  Review of 3SAQS updates to temporal and chemical speciation profiles for nonroad and nonpoint sources

## Slide 9: Key Findings: Emissions
2020 – 2011 Emissions
  Mostly decreases for all sectors/pollutants/states except O&G VOC/TOG
  Plots show differences by state (CO, UT, WY)

## Slide 10: Key Findings: Emissions

## Slide 11: Key Findings: Emissions
Methane
  3SAQS one of the first U.S. regional CTM studies to look at active methane emissions
  Tracer for important regional emissions sectors (O&G and ag)
  O&G is the largest source in the current inventory
  Missing significant agricultural sources: enteric fermentation and livestock waste

## Slide 12
Emissions Reactivity
RTOG = TOG * Profile Total MIR
RTOG/TOG = Relative emission reactivity
Key Findings: Emissions

## Slide 13
Emissions Reactivity
  Reactivity-based analysis of inventories focuses on sources with greatest ozone formation potential
  Different sources are dominant using reactivity weighting vs. mass-based analysis
  Reactivity analysis is dependent on validity of inventory and chemical speciation
Key Findings: Emissions

## Slide 14: Key Findings: Air Quality
2008 Annual 4th Highest Daily Max 8-hour Average O3
Orange is the cutoff for different O3 standards
65 ppb 70 ppb 75 ppb

## Slide 15: Key Findings: Air Quality
2020 Annual 4th Highest Daily Max 8-hour Average O3
Orange is the cutoff for different O3 standards
65 ppb 70 ppb 75 ppb

## Slide 16: Key Findings: Air Quality
4th highest MDA8 O3 decreases up to 25 ppb
Widespread decreases of 1-3 ppb for most of the 3-state region
1-3 ppb increases in O&G development areas
2020 - 2008

## Slide 17: Key Findings: Air Quality
4th highest MDA8 O3 decreases up to 25 ppb
Widespread decreases of 1-3 ppb for most of the 3-state region
1-3 ppb increases in O&G development areas
2020 - 2008

## Slide 18: Key Findings: Air Quality
2008 Annual 4th Highest Daily Max 8-hour Average O3
Orange is the cutoff for different O3 standards
65 ppb 70 ppb 75 ppb

## Slide 19: Key Findings: Air Quality
2011 Annual 4th Highest Daily Max 8-hour Average O3
Orange is the cutoff for different O3 standards
65 ppb 70 ppb 75 ppb

## Slide 20: Key Findings: Air Quality
Annual Average PM2.5
Orange is the cutoff for 12 ug/m3
2008 2020 (2008-based) 2011

## Slide 21: Oil and Gas Emissions Development Activities
2011 base year inventories developed for all major basins in the 3 states
  Uinta (UT)
  Piceance (CO)
  D-J (CO)
  All Wyoming Basins (WY)
  Raton Basin (CO/NM)
  Paradox Basin (UT)
  South San Juan Basin (NM)
2020 projections developed for all basins
2011/2020 emissions processed through SMOKE and model-ready

## Slide 22: Oil and Gas Emissions Development Activities
2011 base year inventories provide updated county-level and by-source category NOx and VOC emissions
Developed by projecting older inventories forward to 2011 considering changes in production and activity, as well as regulatory effects on emission sources
Further projections conducted out to 2020 using historic development trends and forecasts, regulatory effects on inventories
Emissions processed and gridded using SMOKE including industry-specific speciation profiles and detailed spatial allocation of wells and production

## Slide 23: Forecasting Activity to 2020
2020 gas production forecast in the Uinta Basin

## Slide 24: Example Controls Analysis
Federal regulatory controls in the Piceance Basin in 2020

## Slide 25: Oil and Gas Inventory Results for 2011/2020
* Permitted emissions only
Notes: Will update in next base year and future year to reflect new rules that hit the books since the development of this inventory

## Slide 26: Example Emissions by Source Category
2011 NOx emissions by source category in the D-J Basin

## Slide 27: Example Emissions by Source Category
2011 VOC emissions by source category in the D-J Basin

## Slide 28: Example Emissions by County
2011 NOx emissions by county in the Uinta Basin

## Slide 29: Example Processed and Gridded O&G Emissions
June 2011 gridded oil and gas emissions in 4-km modeling domain

## Slide 30: Ongoing Oil and Gas Tasks and Next Steps
Ongoing work
  Data mining of US EPA Tribal Minor New Source Review (MNSR) data on tribal land to improve emissions sources
  Guidance document on incorporation of 3SAQS regional emissions into project analyses
Potential future work
  Improved projection methodologies for midstream and other permitted sources or sources provided by state agencies
  Additional survey efforts to update key source category data in key basins

## Slide 31: Monitoring Network Assessment Recommendations Operations Through 2017
Assessment of ozone monitoring data, meteorology, and unmonitored areas, as well as expected changes in emissions indicate that the existing 3SAQS cooperator group-funded site locations/areas should continue operating through 2017.
Recommending slight changes to some existing site locations, as well as adding new sites.
There are two sets of recommendations, for calendar 2014 and for 2015 to 2017.
Assessment was reviewed and approved by the Steering Committee in May 2014.
  Final assessment materials available on the 3-State Data Warehouse website (http://views.cira.colostate.edu/documents/Projects/TSDW/Projects/MonitoringNetworkAssessment/)
Notes: Steering Committee formed Network Assessment WG for this effort.
Met 10 times October 2013 through Feb. 2014 by phone and at Technical Workshop to conduct Assessment.
Many calls with sub-groups of cooperating agencies.
Note that this was reviewed and approved by the steering committee

## Slide 32: Prototype Web-Based Source Apportionment Visualization Tool
Develop on-line tool for the 3SDW that can visualize ozone and PM source apportionment modeling results
Use WestJumpAQMS state-specific and source category-specific ozone source apportionment results to test the tool
  Daily maximum 8-hour ozone for Geographic (state-specific) and Source Category SA runs
In 3SAQS will expand from 10 highest ozone days to all days and monitors in domain

## Slide 33: SrcApp Visualization Selection
Currently two options

## Slide 34: Select Rocky Flats North, CO on July 9, 2008
 Geographic
 Source Category

## Slide 35: Web-Based SA Visualization Tool
Refine prototype SA visualization tool
Populate with 3SAQS CAMx and CMAQ SA runs when available
  Daily maximum 8-hour ozone and 24-hour PM2.5 concentrations at all monitors in domain
  Annual deposition and daily visibility impairment at IMPROVE monitors
Implement on 3SDW

## Slide 36: Status and Next Steps
Pilot study modeling work status
Plans for October 2014 – April 2015
  2011 CMAQ modeling
  2011 AQ sensitivity modeling
    Boundary Conditions
    Background Air Quality
    Oil & Gas
    Winter Ozone
    Ammonia
    Vertical Transport
    MOVES2014
Reference 9/30 presentation

## Slide 37: 3SAQS Pilot Study Modeling Status
Deliverable | Status
2008 Modeling Platform | 
2008 Modeling Protocol | Completed (4/2014)
SMOKE 36/12-km 2008a | Completed (5/2014)
SMOKE 36/12-km 2008b | Completed (7/2014)
CAMx 36/12-km 2008b | Completed (8/2014)
CAMx 2008a MPE Report | Ready for Review (9/2014)
SMOKE 36/12-km 2020a_08 | Completed (7/2014)
CAMx 36/12-km 2020a_08 | Completed (8/2014)
2011 Modeling Platform | 
2011 Modeling Protocol | Completed (7/2014)
WRF 36/12/4-km 2011a | Completed (5/2014)
WRF 2011 MPE Report | Ready for Review (8/2014)
SMOKE 36/12/4-km 2011a | Completed (8/2014)
CAMx 36/12/4-km 2011a | Completed (9/2014)
CAMx 36/12/4-km 2020a_11 | Running (11/2014)

## Slide 38: 2011 US Background Air Quality
July 2011 US Background