3-State Air Quality Study and Data Warehouse

Technical Committee Recommendation and Discussion Items for Steering Committee

October 10, 2014

+++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++

Data Warehouse

1. Integrate the Date Use Agreement into the Data Request form.
2. Restrict access to the Project Configuration and Data Request forms to a project's team members (and the DW Team).
3. Restrict ftp access on Data Warehouse for modeling platforms that have not been officially released (e.g., 2011a).
4. Provide a link to the Documents page from the main DW home page.
5. Continued development through June 2015 as described.

3-State Regional Modeling

* 3SAQS Base11a MPE Next Steps
	+ 1st Draft Model Performance Evaluation (MPE) report (10/17)
	+ Ozone, PM, and deposition at standard surface networks
	+ Initial review comments by 11/5
	+ 2nd Draft Final MPE report (11/12)
		1. Add UGWOS network
		2. Add vertical ozone profiles
		3. Add NH3
		4. Integrate comments from 1st draft MPE
	+ Technical Committee conference call to review and approve 3SAQS Base11a platform for access on DW (early Dec.)
	+ 3SAQSBase11a platform available on DW (end of Dec.)
* 3SAQS Base2020\_11a platform available for review (mid Dec.)
	+ Review, comment, and Technical Committee approval call (mid-Jan.)
* 3SAQS Base11b work underway in Oct. 2014
	+ Schedule and tasks as discussed through July 2015
	+ Includes updated 2020 projection modeling as well