## Slide 1: Western Air Quality Study (WAQS) Intermountain West Data Warehouse (IWDW)
Revisions to WAQS Phase 2 SoW: September 2015 – March 2016
University of North Carolina (UNC-IE)
Ramboll Environ (RE)
September 23, 2015
Intermountain West Data Warehouse Technical Committee
CIRA/CSU, Fort Collins, Colorado

## Slide 2: IWDW Technical Oversight Committee
July 30, 2015 meeting at NPS/ARD, Denver, Colorado
Decision to revise Scope of Work (SoW) to end of WAQS Phase II contract (Sep 2015 – Mar 2016)
  Do not proceed with developing 2014 PGM platform
    Complete already started 2014 WorkPlan and WRF Modeling
    De-obligate funding from other tasks related to 2014 platform
  Perform additional analysis of 2011 modeling platform
    Additional 2011b model performance evaluation
    CMAQ 2011b 36/12/4 km base case modeling
    CAMx/CMAQ 36/12/4 km future year (FY) modeling
      Need to confirm FY 2025 (and not 2017) by mid-October

## Slide 3: WAQS Phase II SoW
Original WAQS Phase II SoW
  Task 1: 2011 CMAQ (done)
  Task 2: SA Modeling (continue)
  Task 3: Model Improve (done)
  Task 4: 2011 Vis/Dep (done)
  Task 5: 2014 Plan (finish)
  Task 6: 2014 WRF (finish)
  Task 7: 2014 EI (de-obligate)
  Task 8: 2014 AQ (de-obligate)
  Task 9: Winter Ozone (done)
  Task 10: O&G EI (de-obligate)
  Task 11: Management (continue)
New WAQS Phase II SoW
  Task 12: 2011b MPE
  Task 13: CMAQ 2011b
  Task 14: FY SMOKE
  Task 15: FY CAMx
  Task 16: FY CMAQ
FY Determination
  EPA offering 2 FYs based on 2011NEIv2 (EPA platform v2)
    2017 and 2025
  2017 available now (Jul 2015)
  2025 available Oct 2015?
  IWDW-WAQS TechComm makes recommendation today

## Slide 4: Original WAQS Phase II SoW
Task 1: 2011 CMAQ Modeling
  Objectives: Develop and evaluate CMAQ modeling platform using 2011a database
    Develop CMAQ 2011a 4 km database (Jan `15)
    Add CMAQ MPE to 2011a MPE Report (Mar `15)
    Finalize 2011a MPE Report post to IWDW (Apr `15)
Task 2: Source Apportionment Modeling
  Objectives: To quantify emission source/receptor relationships in western U.S. using 2011 database
    Geographic (state-specific) SA run using 2011a (Jun-Aug ’15)
    Wait for 2011b EI for source-category and detailed SA runs

## Slide 5: Original WAQS Phase II SoW
Task 3: AQ Model Improvements
  Objectives: Use air quality model sensitivity tests to improve 2011a model performance leading to 2011b
    Draft (Nov ’14) and Final (Jun ’15) 2011a MPE Reports
    Much additional analysis performed
    Task segues to New Task 12
Task 4: 2011 Vis/Dep Evaluation
  Objective: Provide more detailed assessment of 2011 platform visibility/deposition assessment
    IMPROVE equation for visibility evaluation
    NADP for wetdep SO4, NO3 and NH4
    Questions on reliability of CASTNet drydep “observations”

## Slide 6: Original WAQS Phase II SoW
Task 5: 2014 Modeling Plan
  Objective: To develop modeling and data analysis plan for simulating 2014 Calendar year
    Draft 2014 Plan prepared (Jul `15)
Task 6: 2014 WRF Modeling
  Objective: To generate WRF 2014 meteorological data for 36/12/4 km domains
Task 7: 2014 Emissions (de-obligate)
Task 8: 2014 CAMx/CMAQ (de-obligate)

## Slide 7: Original WAQS Phase II SoW
Task 9: Winter Ozone Modeling
  Objectives: To develop an operational winter ozone modeling configuration for WRF for use with CAMx/CMAQ.
    Prepare WRF winter modeling Memo & wiki (Jul `15)
Task 10: O&G Emissions
  Objectives: Update 2011 and develop surveys for 2014 O&G emissions
    Update 2011b O&G EI
    De-obligate remaining funds for new Tasks

## Slide 8: Original WAQS Phase II SoW
Task 11: Project Management
  Objectives: Conference calls, meetings, monthly reports, contracts and manage study
Summary of Original SoW Funding (9/1/15)
Retain 5 Tasks from original WAQS Phase II SoW

## Slide 9: WAQS Work Sep ’15 – Mar ‘16
Task 2: Source Apportionment (SA) Modeling
  Geographic (state-specific) SA w/ 2011a
    Ozone & PM SA 2011a 36/12 km (Jul-Sep `15)
      Post-process implement visualization tool (Sep-Oct `15)
  Source Category SA w/ 2011b
    Ozone SA 2011b 36/12 km (Sep-Oct `15)
    PM SA 2011b 36 km (Sep-Oct `15)
  Detailed SA using 4 km 3SAQS domain
    Ozone SA 2011b 4 km (Nov `15)
    PM SA 2011b 4 km (Nov-Dec `15)
  Post-process and transfer to IWDW (Jan-Feb `15)

## Slide 10: WAQS Work Sep ’15 – Mar ‘16
Task 5: 2014 WRF
  Complete WRF 2014 36/12/4 km run and MPE
  WRF 2014 36/12/4 km Application/Evaluation Report
Task 10: O&G Emissions
  Document work done to date and transfer to IWDW
Task 11: Project Management
  Continue project management to Feb ‘16

## Slide 11: WAQS Work Sep ’15 – Mar ‘16
New Task 12: Complete 2011b MPE Analysis
  Objective: Finish CAMx 2011b MPE and incorporate CMAQ 2011b MPE
    2011b Protocol Addendum (Sep ‘15)
    2011b MPE Addendum and wiki (Oct ’15)
    EI Trends Report (Oct ’15)
    Winter Ozone Summary/Recommendations (Nov ’15)
    O&G Summary/Recommendations (Nov ’15)
    Data transfer to IWDW (Nov ’15)

## Slide 12: WAQS Work Sep ’15 – Mar ‘16
New Task 13: CMAQ 2011b 36/12/4 km Base Case
  Objective: Perform CMAQ 2011b 36, 12 and 4 km base case and MPE
    Conduct CMAQ 2011b 36, 12 and 4 km Run (Nov ’15)
    Integrate in 2011b MPE Addendum and wiki (Dec ’15)
New Task 14: FY SMOKE EI Modeling 2011b
  Objective: Process selected FY emissions using SMOKE
    CAMx/CMAQ-ready FY emission inputs (Dec ’15)
    EI Trends Report Addendum (Jan ’16)
    Transfer FY EI to IWDW (Jan ’16)

## Slide 13: WAQS Work Sep ’15 – Mar ‘16
New Task 15: CAMx FY 36/12/4 km Modeling
  Objective: Perform CAMx FY Modeling
    CAMx FY 36/12/4 km Run (Feb ’16)
    FY Modeling Report (Mar ’16)
    Transfer FY CAMx to IWDW (Mar ’16)
New Task 16: CMAQ FY 36/12/4 km Modeling
  Objective: Perform CMAQ FY Modeling
    CMAQ FY 36/12/4 km Run (Feb ’16)
    FY Modeling Report (Mar ’16)
    Transfer FY CMAQ to IWDW (Mar ’16)

## Slide 14: WAQS Work Sep ’15 – Mar ‘16
New Task 17: IWDW Support
  Objective: Provide air quality modeling expertise support to IWDW
    Weekly IWDW operation conference calls
    Additional topical conference calls
    IWDW data support
    IWDW programming and documentation support
    Data storage and hardware

## Slide 15: WAQS Project Timeline
2015
DEC 2014- APR 2015
Base11a MPEv2
JAN-MAR
CMAQ Base11a
JAN-APR
WRF Winter Modeling Configuration
MAR-JUN
2011b Emissions Development
SEP
2011b CAMx MPE
JUN-AUG
2011b CAMx
Modeling
SEP 23, 2015
Technical Comm Meeting
NOV 2015
Release CAMx 2011b
DEC
2011b CMAQ
April 29-30
Tech Comm Call
MAY
Base2011a Platform Release; MOVES and Winter O3 CAMx Complete
APR
Phase II O&G EI Release
MAY-AUG
2014a WRF and SMOKE
JAN 21
Governing
Board Meeting
FEB 25, 2015
Technical Comm Meeting
JUL 2015
Technical Comm Call
SEP -FEB
2011b SA Modeling
OCT-MAR
FY CAMx &
CMAQ Modeling
Notes: In 2012 much of the work was focused on transitioning from the WestJumpAQMS 2008 modeling platform to the 3SAQS 2008 platform, including identifying areas of improvement in the inventories and defining the specifications of the modeling.
2013 began with targeted meetings with each of the 3-states to review proposed improvements to the inventories and to gather additional data/information to use for the 3SAQS emissions modeling; at the suggestion of EPA Region 8, analysis of the VOC inventories used information on VOC reactivity to focus on sources most important to ozone formation in the region; we performed a preliminary 2008 CAMx simulation and evaluation (version A). A series of WRF sensitivities were conducted to evaluate the Western Regional Modeling configuration and to identify any options that could be changed to improve model performance; these were done toward finding the optimal configuration for 3SAQS; monitoring network assessment was started and series of meetings were held to review the interim progress; 2011 O&G EI development started
2014 Monitoring network report was developed and released for review, by May the recommendations in this report were approved by the Steering Committee; second version of the 2008 emissions with corrections to onroad mobile sources (replaced WestJump inventory with EPA MOVES emissions factor mode data); CAMx 2008b was finished and evaluated; 2011 WRF, emissions modeling, and CAMx were completed; WRF 2011 MPE report is out for comment and the CAMx evaluation is underway now; future year (2020) simulations for both base years were completed and a series of sensitivity simulations based off of the 2011 modeling are also underway or planned
Completed modeling results and data, scripts, model codes were loaded on the 3SDW servers for distribution to cooperators