## Slide 1: Three-State Air Quality Study (3SAQS) Three-State Data Warehouse (3SDW)
3SAQS 2015 Scope of Work
University of North Carolina (UNC-IE)
ENVIRON International Corporation (ENVIRON)
September 30, 2014

## Slide 2: Three-State Air Quality Study (3SAQS) 2015 Scope of Work (SOW)
Covers period of October 1, 2014 through July 31, 2015
Contracted through WESTAR
  Tom Moore, Technical Director
ENVIRON International Corporation – Prime
  Ralph Morris, Project Manager
University of North Carolina, Institute for Environment -- Subcontractor
  Zac Adelman, Project Manager

## Slide 3: 3SAQS Pilot Study 2011 CAMx Platform
36 km CONUS; 12 km WESTUS; 4 km 3SAQS

## Slide 4: Task 1: 2011 CMAQ Modeling
CMAQ V5.0.2 2011a 36/12/4 km Base Case Modeling
  Use “same” inputs as current CAMx 2011a Base Case
    MOZART or GEOS-Chem BCs; WRF processed with MCIP meteorology; 2011a Base Case emissions
  Annual 2011 CMAQ 36, 12 and 4 km one-way nesting
    (CAMx used two-way nesting)
    Model Performance Evaluation
Deliverables:
  2011 CMAQ 36/12/4 km I/O loaded on 3SDW
  CMAQ MPE report and comparison to CAMx MPE
  3SAQS guidance document on how/when use CMAQ vs. CAMx
Schedule: Oct - Nov 2014

## Slide 5: Task 2: 2011 Source Apportionment Modeling (1 of 2)
2a: Source Apportionment (SA) Design
  Review and comment from 3SAQS TechComm
2b: CAMx 2011 36/12 km Geographic SA
  State-specific, BCs, EUSA, Can, Mex, Off-shore
  Post-process: CSAPR-type, on-line SA web tool, etc.
2c: CAMx 2011 36/12/4 km Emissions Sector SA
  SA by major source categories
  E.G., EGU, other Points, On-road, Non-road, O&G, etc.
  Post-process model results

## Slide 6: Task 2: 2011 Source Apportionment Modeling (2 of 2)
2d: CAMx detailed SA using 4 km 3SAQS Domain
  Geographic (e.g., by Basins) and Source Sectors
2e: SA Web Tool on 3SDW
  Functionality similar to WestJumpAQMS Spreadsheets only all days instead of just top 10 days
2f: CMAQ SA Modeling
  Geographic like 2b only just using 36 km CONUS domain
    For some days CAMx 36 km SA to help interpret differences
  Detailed SA 4 using 4 km domain like 2d
Deliverables:
  SA Design Document
  SA Results loaded in web-based visualization tool
  SA report on results and how to use/interpret SA results
Schedule: Oct 2014 – Apr 2015

## Slide 7: Task 3: 2011 Model Improvements (1 of 6)
Perform CAMx and/or CMAQ sensitivity tests for all or part of 2011 to investigate model performance issues and/or alternative inputs/options
  Model Performance Evaluation (MPE)
If improved performance is seen, may adopt as new 2011 base case
First set of sensitivity tests performed using 2013-2014 Pilot Study funding

## Slide 8: Task 3: 2011 Model Improvements (2 of 6)
GEOS-Chem Boundary Condition (BC) [Pilot]
  Compare with results using MOZART BCs
  Dust and ozone BC tracers
  CAMx 36/12/4 km 2011 annual run
  MPE including ozonesonde, STE events and spring dust
  Adopt as new 2011 Base Case if improved MPE
US Background AQ using MOZART BCs [Pilot]
  CAMx 2011 36/12 km annual with zero US anthropogenic emissions
  Calculate background ozone with no US anthro

## Slide 9: Task 3: 2011 Model Improvements (3 of 6)
Oil and Gas VOC Sensitivity [Pilot]
  Literature review to obtain top down VOC scaling factors for each O&G Basin
  Adjust 2011 O&G VOC emission by Basin
  CAMx 2011 with adjusted VOC O&G simulation
  Conduct MPE and compare with 2011 Base Case
Preliminary Winter ozone sensitivity [Pilot]
  May use new winter WRF simulations performed under Task 9
  CAMx and/or CMAQ sensitivity to O&G VOC, snow cover, albedo, mixing, etc.

## Slide 10: Task 3: 2011 Model Improvements (4 of 6)
Ammonia Emissions Sensitivity [Pilot]
  Work with NPS/ARD to develop ammonia sens test
  Use AMON observations, satellite data etc. to develop changes in temporal, spatial and magnitude of NH43 emissions
  CAMx and/or CMAQ sensitivity for portion of 2011
Optional US Background using GEOS-Chem BCs [Pilot]
  CAMx 2011 36/12 km annual with zero US anthropogenic emissions
  Calculate background ozone with no US anthro
  Compare with MOZART US Background run

## Slide 11: Task 3: 2011 Model Improvements (5 of 6)
Oil and Gas Emissions [2015 SOW]
  Design 2-3 emission sensitivity to adjust O&G emissions in specific Basins to improve MPE
  Link to literature review of top down adjustments
Vertical Transport/Mixing [2015 SOW]
  Explore alternative vertical transport and mixing approaches including no WRF layer collapsing using CAMx and/or CMAQ for portion of 2011
MOVES2014 on-road mobile sources [2015 SOW]
  MOVES2014 released 7/31/14, SMOKE-MOVES2014 in Oct?
  Use SMOKE-MOVES2014 to generate new on-road emissions for 36/12/4 km 3SAQS domains
  Compare emissions w/ MOVES2010b for 3SAQS domains
  CAMx 2011 MOVES2014 annual Base Case and MPE
  Compare CAMx MPE using MOVES2014 vs. MOVES2010b

## Slide 12: Task 3: 2011 Model Improvements (6 of 6)
CAMx 2011b Base Case modeling
  Integrate model improvements in CAMx emissions and other inputs
  Conduct CAMx 2011b 36/12/4 km base case and MPE
Deliverables:
  Work Plan describing sensitivity tests to be performed
  PowerPoint presentations on each sensitivity test
  Memorandum on all sensitivity tests and 2011b updates
  Updated CAMx 2011b base case I/O loaded on 3SDW
Schedule: Oct 2014 – Mar 2015

## Slide 13: Task 4: Deposition and Visibility Analysis
Provide more detailed analysis of 2011 visibility and deposition MPE
  Analyze CAMx/CMAQ visibility performance using direct measurements as well as reconstructed mass
  Wet deposition MPE (NADP) and dry deposition “MPE” (CASTNet)
Deliverables: Document describing CMAQ and CAMx 2011 visibility and deposition analysis and how it will be used to improve the 2014 application
Schedule: Dec 2014 – Mar 2015

## Slide 14: Task 5: 2014 Data Analysis/Modeling Plan
Develop a plan for how the preliminary 2014 modeling will be conducted
Deliverables:
  2014 Modeling Plan overview
  Document on Lessons Learned from 3SAQS 2008 and 2011 SMOKE/WRF/CAMx/CMAQ modeling
Schedule: Jan – Feb 2015

## Slide 15: Task 6: 2014 WRF Modeling
Apply WRF for 2014 36/12/4 km
  Use two WRF configurations
    Standard configuration like 3SAQS with updates
    Wintertime configuration based on Task 9
  Model Performance Evaluation
    Surface, Upper-Air, Mixing Heights, Precipitation
Deliverables:
  WRF 2014 Modeling Protocol
  2014 WRF I/O and displays loaded on 3SDW
  WRF 2014 Model Application/Evaluation Report
Schedule: Mar – May 2015

## Slide 16: Task 7: Preliminary 2014 Emissions (1 of 2)
Why not wait for 2014 NEI?
  EPA getting better but still delays in releasing NEIs
    2008 NEI V1 Apr 2012 – 40 months after year
    2011 NEI V1 Sep 2013 – 21 months after year
  Performing preliminary 2014 emissions and AQ modeling will allow an evaluation of other components of the modeling system and provide time for model improvements
    Meteorology, boundary conditions, etc.
  Also allow development of 2014 O&G emissions that can feed 2014 NEI
Preliminary 2014 emissions and SMOKE modeling
  Keep simple, 2014prelim will have short shelf life
  O&G from Task 10 preliminary 2014 O&G
  SMOKE-MOVES2014 with 2014 VMT and WRF data

## Slide 17: Task 7: Preliminary 2014 Emissions (2 of 2)
Preliminary 2014 emissions and SMOKE modeling
  2014 CEMs data for large EGUs
  2011 NEI projected to 2014
  MEGAN biogenic emissions using 2014 WRF
  Ammonia using 3014 CAFOs etc. and CMU model
  Use best available source for fires (FINN?)
Deliverables:
  2014prelim development plan
  SMOKE 2014prelim I/O loaded on 3SDW
  Emission trends report comparing 2008/2011/2014
  Annual 2014prelim 36/12/4 km CMAQ/CAMx emission inputs
  Memo on 2014prelim emissions and recommendations for improvements
Schedule: Mar – Jun 2015

## Slide 18: Task 8: Preliminary 2014 AQ Modeling
Prepare CMAQ/CAMx 2014 Modeling Protocol
Conduct CMAQ/CAMx preliminary 2014 36/12 km modeling
  Add in 4 km domain later with improved emissions
  Model Performance Evaluation
  Recommend model improvements
Deliverables:
  CMAQ/CAMx 2014 Modeling Protocol
  CMAQ/CAMx 2014 I/O and MPE displays loaded on 3SDW
  Report on CMAQ/CAMx preliminary 2014 modeling and MPE
  3SAQS air quality/deposition/visibility trends report comparing 2008, 2011 and 2014
Schedule: May – Jul 2015

## Slide 19: Task 9: WRF Winter Ozone Modeling
9a: Winter Ozone Work Plan
  Review winter ozone field and modeling studies
9b: Develop WRF winter ozone period configuration
9c: Evaluate 3SAQS WRF configuration for Feb 1-7, 2013 benchmark
  Uinta Basin
9d: Simulate 2011 winter ozone periods with 3SAQS WRF configuration
  Uinta Basin and JPAD area
  CAMx/CMAQ sensitivity tests under Task 3
9e: Winter WRF Modeling Memo
9f: Additional WRF for other winter ozone events
Deliverables:
  WRF Work Plan for winter ozone modeling
  3SAQS WRF 2011 winter ozone modeling I/O and MPE results on 3SDW
  Final WRF winter ozone modeling memorandum
Schedule: Oct 2014 – Feb 2015

## Slide 20: Task 10: O&G Survey and Preliminary 2014 Emissions (1 of 2)
Survey O&G Operators in Piceance Basin and Unita Basin
  WRAP Phase III survey for 2006 out-of-date
    Significant changes in industry practices since then
  WDEQ has O&G inventory for whole state
    No survey needed as O&G inventory judged complete
  Denver-Julesburg survey under separate study (RPSEA)
Perform outreach to Operators to make sure surveys are responded to (Airstar)
Acquire 2014 O&G “permitted” O&G data from states and EPA (tribes)
  Colorado 2014 APEN data
  Utah mainly tribal data obtained from EPA
  Wyoming has complete O&G inventory

## Slide 21: Task 10: O&G Survey and Preliminary 2014 Emissions (2 of 2)
Project “unpermitted” O&G emissions to 2014
  For Colorado and Utah only
  Start with 3SAQS 2011 O&G emissions
  Assume new 2014 survey data will not be available
Format preliminary CO-UT-WY 2014 O&G for SMOKE
Deliverables:
  Plan for developing preliminary 2014 O&G emissions for 3 States
  Basin-aggregated survey data on activity, equipment, processes, gas composition, etc.
  Preliminary 2014 O&G emissions for 3SAQS formatted for SMOKE
  Memo on development of preliminary 2014 O&G emissions
  Memo on how to implement new NEPA future year Project O&G emissions with 3SAQS O&G emission inventories
    Also discusses design of on-line tool that compares Project O&G emissions with 3SAQS future year O&G emission inventories
Schedule: Oct 2014 – Jun 2015

## Slide 22: Task 11: Project Management
Attend conference calls and project meetings
Interact with 3SDW contractors
Prepare contracts and monthly progress reports and invoices
Perform project management
Deliverables:
  Signed Contracts and Subcontracts
  Monthly progress reports and invoices
  Attend conference calls and meetings
Schedule: Oct 2014 – Jul 2015

## Slide 23: Questions?
3SAQS 2015 SOW
Oct 1, 2014 – Jul 31, 2015