## Slide 1: Three-State Air Quality Study (3SAQS) Three-State Data Warehouse (3SDW)
3SAQS Modeling Schedule
Winter 2014-Spring 2015
University of North Carolina (UNC-IE)
ENVIRON International Corporation (ENVIRON)
September 30, 2014

## Slide 2: Overview
Pilot study modeling work status
Plans for October 2014 – April 2015
  2011 CMAQ modeling
  2011 AQ sensitivity modeling
    Boundary Conditions
    Background Air Quality
    Oil & Gas
    Winter Ozone
    Ammonia
    Vertical Transport
    MOVES2014
List of tasks, deliverables, and expected dates

## Slide 3: 3SAQS Pilot Study Modeling Status
Deliverable | Status
2008 Modeling Platform | 
2008 Modeling Protocol | Completed (4/2014)
SMOKE 36/12-km 2008a | Completed (5/2014)
SMOKE 36/12-km 2008b | Completed (7/2014)
CAMx 36/12-km 2008b | Completed (8/2014)
CAMx 2008a MPE Report | Ready for Review (9/2014)
SMOKE 36/12-km 2020a_08 | Completed (7/2014)
CAMx 36/12-km 2020a_08 | Completed (8/2014)
2011 Modeling Platform | 
2011 Modeling Protocol | Completed (7/2014)
WRF 36/12/4-km 2011a | Completed (5/2014)
WRF 2011 MPE Report | Ready for Review (8/2014)
SMOKE 36/12/4-km 2011a | Completed (8/2014)
CAMx 36/12/4-km 2011a | Completed (9/2014)
CAMx 36/12/4-km 2020a_11 | Running (11/2014)

## Slide 4: 2011 CMAQ Modeling
CMAQ V5.0.2 2011a 36/12/4 km Base Case Modeling
  Use “same” inputs as current CAMx 2011a Base Case
    MOZART or GEOS-Chem BCs; WRF processed with MCIP meteorology; 2011a Base Case emissions
  Annual 2011 CMAQ 36, 12 and 4 km one-way nesting
    (CAMx used two-way nesting)
    Model Performance Evaluation
Deliverables:
  2011 CMAQ 36/12/4 km I/O loaded on 3sDW
  CMAQ MPE report and comparison to CAMx MPE
  3SAQS guidance document on how/when use CMAQ vs. CAMx
Schedule: Oct - Nov 2014

## Slide 5: 2011 Sensitivity Modeling
Perform CAMx and/or CMAQ sensitivity tests for all or part of 2011 to investigate model performance issues and/or alternative inputs/options
Boundary Condition Sensitivity
  GEOS-Chem Boundary Condition (BC)
  Compare with results using MOZART BCs
  Dust and ozone BC tracers
  CAMx 36/12/4 km 2011 annual run
  MPE including ozonesonde, STE events and spring dust
  Adopt as new 2011 Base Case if improved MPE

## Slide 6: 2011 Sensitivity Modeling
Background Air Quality
  US Background AQ using MOZART BCs
    CAMx 2011 36/12 km annual with zero US anthropogenic emissions
    Calculate background ozone with no US anthro
    Status: running now
  Optional US Background using GEOS-Chem BCs
    CAMx 2011 36/12 km annual with zero US anthropogenic emissions
    Only do this if differences between MOZART and GEOS-Chem base runs

## Slide 7: 2011 Sensitivity Modeling
Oil and Gas VOC Sensitivities
  Literature review to obtain top down VOC scaling factors for each O&G Basin
  Adjust 2011 O&G VOC emission by Basin
  Design 2-3 additional emission sensitivities to adjust O&G emissions in specific Basins to improve MPE
  CAMx 2011 with adjusted VOC O&G simulation

## Slide 8: 2011 Sensitivity Modeling
Preliminary Winter ozone sensitivity
  May use new winter WRF simulations
  CAMx and/or CMAQ sensitivity to O&G VOC, snow cover, albedo, mixing, etc.
Ammonia Emissions Sensitivity
  Work with NPS/ARD to develop ammonia sens test
  Use AMON observations, satellite data etc. to develop changes in temporal, spatial and magnitude of NH3 emissions
  CAMx and/or CMAQ sensitivity for portion of 2011
  Ideas:
    Integrated process rate (process analysis) simulation at AMON and Boulder, CO monitoring sites
    CMAQ bi-directional NH3 flux sensitivity (with vs without bi-di)

## Slide 9: 2011 Sensitivity Modeling
Vertical Transport/Mixing
  Explore alternative vertical transport and mixing approaches, including no WRF layer collapsing, using CAMx and/or CMAQ for portion of 2011
MOVES2014 on-road mobile sources
  MOVES2014 released 7/31/14, SMOKE-MOVES2014 in Oct?
  Use SMOKE-MOVES2014 to generate new on-road emissions for 36/12/4 km 3SAQS domains
  Compare emissions w/ MOVES2010b for 3SAQS domains
  CAMx 2011 MOVES2014 annual Base Case and MPE
  Compare CAMx MPE using MOVES2014 vs. MOVES2010b

## Slide 10: 2011 Sensitivity Modeling
CAMx 2011b Base Case modeling
  Integrate model improvements in CAMx emissions and other inputs
  Conduct CAMx 2011b 36/12/4 km base case and MPE
Deliverables:
  Work Plan describing sensitivity tests to be performed
  PowerPoint presentations on each sensitivity test
  Memorandum on all sensitivity tests and 2011b updates
  Updated CAMx 2011b base case I/O loaded on 3SDW
Schedule: Oct 2014 – Mar 2015