## Slide 1
 | Tasks | Timeframe
1 | Regional Haze Monitoring Data Analysis for 2014 IWDW-WAQS MPE / 2000 through 2016 Planning Metric options (2 rounds) | #1 complete Oct. 2018 #2 complete Sept. 2019
2 | Dynamic Model Evaluations for Regional Haze Progress to date (some combination of WRAP Plan02d, 2008 WestJumpAQMS, IWDW-WAQS 2011b, new 2014 IWDW-WAQS platform, WRAP PRP18b) | complete Oct. 2018
3, 4, 5, 6 | 2014 Base Year Emissions Processing, Met Modeling/MPE, Global Modeling/MPE, Regional Air Quality Modeling/MPE | complete Sept. 2018
7 | IWDW-WAQS Air Quality Modeling for Planning – develop 2013-17 regional baseline / consider use of 2016 Emissions Modeling Platform national collaborative / 4 Corners Study / coordinate with EPRI International Haze Study (as these products are available) | from Nov. 2018 through Sept. 2019
8 | 2023 and 2028 On-The-Books Emission Projections | complete Feb. 2019
9 | IWDW-WAQS 2023 and 2028 On-The-Books Air Quality Modeling | complete April 2019
10 | IWDW-WAQS Future Year(s)’ Source Apportionment and Sensitivity Modeling / Regional Haze Control Scenarios* | May 2019 through early 2020*
11 | IWDW Data & Documentation Delivery (two-sided task) ** | July 2018 through early 2020
 | * as resources permit and regional analysis completion schedule allows ** data from modeling / other analyses - Regional Haze Planning / regional analysis support in 2018-19 – combined effort of modeling contractor and IWDW teams | 
Ancillary Study A | Arizona border ozone modeling study (similar scope to: https://www.wrapair2.org/SNMOS.aspx) | timeframe in 2018-19 to be determined
Option B | Denver/Northern Front Range RAQC ozone modeling platform development (align with RAQC contracting decisions as possible) | timeframe in 2018-19 to be determined
Western Regional Modeling Platform - Analysis Tasks and Schedule
for WESTAR Request for Proposal
June 20, 2018