## Readme
DRAFT - This document is being developed by WESTAR-WRAP, the WAQS-IWDW, and the WRAP modeling contractor
Western Regional Modeling and Analysis Platform | Timeframe
This document outlines a process for the interaction between IWDW and modeling contractor (and subcontractors) for the WRAP's 2014 base and future year modeling efforts. Due to the division of tasks among modeling contractors, particularly with respect to emissions processing, and the importance of having all the "pieces" of the modeling effort fit toghether at the end of each modeling round, the IWDW is providing tracking and coordination for the modeling.
2014 v1 | Feb. 2019
A 3-month work effort (December 2018 – early March 2019) to shake-out an initial 2014 PGM modeling platform. This initial modeling round will perform sensitivity analyses, including evaluation of EPA and WAQS WRF modeling, and inputs from MEGAN and BEIS biogenics models. Emissions inputs are based on the 2014 NEIv2 with updates from the WRAP RHPWG EI & MP Subcommittee. | Modeling Plan (Jan. 2019) Dynamic model evaluations (Spring 2019)
2014 v2 | Spring 2019
The second round of WRAP modeling will incorporate O&G updates from the WRAP O&G Work Group, 2014v2 files from the WRAP Fire & Smoke WG, a wholesale update of anthropogenics emissions from CARB
IWDW-WAQS Air Quality Modeling for Planning – develop 2013-17 regional baseline | Feb. 2019 through early 2020
2023 and 2028 On-The-Books Emission Projections (maybe also 2020) and AQ Modeling | Early Summer 2019
AQ modeling August 2019
IWDW-WAQS Future Year(s)’ Source Apportionment and Sensitivity Modeling / Regional Haze Control Scenarios* | Summer 2019 through early 2020*
IWDW Data & Documentation Delivery (two-sided task) ** | Late 2018 through early 2020
Resources
WAQS 2014 Modeling Platform wiki: http://views.cira.colostate.edu/wiki/wiki/9194/waqs-2014-modeling-platform
WRAP RHPWG EI&MP Subcommittee: http://views.cira.colostate.edu/wiki/wiki/9191
WRAP O&G Work Group: https://www.wrapair2.org/ogwg.aspx
WRAP Fire and Smoke WG: https://www.wrapair2.org/FSWG.aspx
Questions:
Explain Air Sci tasks for fire processing v1 vs. v2
Will UNC produce unmerged gridded emissions, then Ramboll will merge these to PGM model ready files?
* as resources permit and regional analysis completion schedule allows
** data from modeling / other analyses - Regional Haze Planning / regional analysis support in 2018-19 – combined effort of modeling contractor and IWDW teams

## WRAP 2014v1 Base Year
Table 2. Process for WRAP 2014 Base Year (v1) modeling, including file transfers between the IWDW and modeling contractor(s).
Modeling Component | File Transfer | Date | Processing | Files | Comments | Criteria before moving to next step | Target Completion Date
Meteorology | IWDW→Ramboll | Sent 11/16/2018; Rec'd 11/20/2018 | Ramboll | WAQS 2014 (36km, 12km, 4km, WRF, WRFCAMx, MCIP) WRF v3.6.1 | Evaluate WAQS 12km met. model performance in WUS for met fields and PRISM precip |  | Jan. 15, 2019
| IWDW→Ramboll | Sent 11/16/2018; Rec'd 11/20/2018 | Ramboll | EPA 2014 (WRF 12km CONUS) WRF v3.8 | Ramboll generates 12km WRFCAMx, MCIP and returns to IWDW. Evaluate met fields, as above. |  | Jan. 15, 2019
| Ramboll→IWDW |  |  | EPA 2014 (WRFCAMx, MCIP) | Ramboll return model ready EPA met files to IWDW
Global Model | IWDW→Ramboll | Sent 11/16/2018; Rec'd 11/20/2018 |  | EPA 2014 GEOS-Chem output
| Ramboll→IWDW |  | Ramboll | CAMx/CMAQ ready BCs | Ramboll generates CAMx/CMAQ ready BCs |  | Jan. 15, 2019
| Ramboll→IWDW |  | Ramboll | Software/scripts to generate model ready BCs from global model output | Not sure if we need/want these
Emissions | IWDW→UNC |  |  | RHPWG EI&MP 2014 EI updates for WRAP states | RHPWG EI & MP Subcommittee will merge and reformat updates before sending to UNC
| EPA→UNC |  |  | 2014 NEI v2 Modeling platform inputs/SMOKE utilities | EPA's 2014 NEIv2 modeling platform files (latest version is 2014v7.2) are available at ftp://newftp.epa.gov/Air/emismod/2014/v2/
|  |  | UNC | UNC merges WRAP (v1) EI updates with 2014 NEIv2 | v1 will incorporate CA updates provided to EI&MP Subcommittee. WRAP 2014 v2 modeling will incorporate a full anthropogenic sector update that CA will provide by Feb., 2019
|  |  | UNC | SMOKE emissions processing for anthro. sectors for WAQS 36km CONUS domain and new 12km western U.S. domain
|  |  | UNC | SMOKE emissions modeling of 2014NEIv2 with WRAP v1 updates for 12/36km domains
|  |  | UNC | Generate unmerged gridded emissions |  | define sectors for unmerged emissions files
|  |  | UNC | CAMx/CMAQ model ready emissions | Done by Ramboll? UNC only generates unmerged emissions? | Make sure model ready emissions are suitable for current CAMx/CMAQ versions
|  |  | UNC | Custom smoke report for IWDW |  | Specify sectors/pollutants retained in reports; output file format
|  |  | UNC | Ancillary data | Spatial surrogates; temporal profiles; speciation profiles used for SMOKE processing
|  |  | UNC | QA summaries
| UNC→IWDW |  |  | Unmerged gridded emissions; IWDW smoke reports; ancillary data; QA summaries
| EPA→Ramboll |  |  | Emissions inputs for natural source sectors
|  |  | Ramboll | MEGANv3 biogenic emissions modeling for 2014 on 36/12km domains. | Potentially BEIS biogenic emissions modeling for 2014 on 36km domain (12km BEIS model-ready inputs are already available)
|  |  | Ramboll | Sea salt, DMS, Lightning NOx, WBD for 2014 on 36/12km domains
| EPA→AS |  | AS | Update 2014 NEIv2 fire emissions. (For example, fire type (WF, WX, Ag), plume rise, diurnal variation, speciation ,etc. | EPA's 2014 NEIv2 modeling platform files (latest version is 2014v7.2) are available at ftp://newftp.epa.gov/Air/emismod/2014/v2/ | What are Air Sci tasks for v1 vs. v2 fire processing
| AS→IWDW→Ramboll |  |  | Modeled Fires
|  |  | Ramboll | Processing of modeled fires
| UNC→IWDW→ Ramboll |  |  | Unmerged gridded emissions
|  |  | Ramboll | Combine UNC processed anthro. emissions, AS fire emissions, and Ramboll natural emsisions; generate CAMx/CMAQ model ready emissions on 36/12km domains
| Ramboll→IWDW |  |  | Complete set of emissions inputs, ancillary data (spatial surrogates, speciation profiles) model ready emissions; QA summaries |  |  | Jan. 31, 2019
PGM |  |  | Ramboll |  | Set up CAMx/CMAQ 36km NA, 12km CONUS for 2014
|  |  | Ramboll |  | WAQS vs EPA WRF sensitivity
|  |  | Ramboll |  | MEGAN vs. BEIS sensitivity
|  |  | Ramboll |  | AQ modeling sensitivity; how does modeling affect pockets of NAAs in western states, etc. |  | Feb. 28, 2019
|  |  | Ramboll |  | 2014 annual CAMx and CMAQ 36/12km simulations using preferred configuration
|  |  | Ramboll |  | Generate MPE products using AMET | Specify other MPE analysis tools, scope of MPE products
| Ramboll→IWDW |  |  | O3 column, chem, tuv, landuse, ocean (CMAQ) | Transfer “other” inputs required for PGM modeling
| Ramboll→IWDW |  |  | PGM output | CAMx/CMAQ 3D conc., deposition output
| Ramboll→IWDW |  |  | MPE products | AMET scripts, MySQL db, AQOBS | Other MPE products? | Feb., 2019
|  |  | IWDW | MET, PGM output | MPE using AMET and other tools

## WRAP 2014v2 Base Year
Table 2. Process for WRAP 2014 Base Year (v2) modeling, including file transfers between the IWDW and modeling contractor(s).
Modeling Component | File Transfer | Date | Processing | Files | Comments | Criteria before moving to next step | Target Completion Date
Meteorology | IWDW |  |  | 36km/km12km WRFCAMx, MCIP | Generated by Ramboll in v1 modeling round
Boundary Conditions | IWDW |  |  | CAMx/CMAQ ready BCs | Generated by Ramboll in v1 modeling round using EPA's 2014 GEOS-Chem output
Emissions | IWDW→UNC |  |  | WRAP 2014 v2 EI updates: 1. Wholesale update of anthropogenic sectors from CARB 2. 2014v2 fires from the WRAP Fire & Smoke WG (from Matt) 3. Oil & Gas WG (from Ramboll) 4. Mobile source updates from CO, other states? 5. Fixing errors from v1 QA, for v2. | CARB plans to provide emissions updates as PGM model ready inputs. These are not deliniated by state/county and will need to be processed to the state/county to update the WRAP emissions dataset. (is this statement accurate?) CA will provide both 2014 and 2028 emissions. |  | Feb., 2019 (date to receive CA updates)
|  |  | UNC | SMOKE emissions processing/modeling for anthro. sectors for 36km/12km domains
|  |  | UNC | Generate unmerged gridded emissions; CAMx/CMAQ model ready emissions |  | confirm that v1 unmerged emissions sectors are appropriate for v2
|  |  | UNC | Custom smoke report for IWDW |  | Specify any modifications from v1. Can UNC provide report specific to sectors that changed from v1, rather than compete v2 EI?
|  |  | UNC | Ancillary data | Spatial surrogates; temporal profiles; speciation profiles used for SMOKE processing | Only necessary if there were chages from v1
|  |  | UNC | QA summaries | Will need a complete MPE for the 2014v2 modeling scenario
| UNC→IWDW |  |  | WRAP 2014v2 EI files; unmerged gridded emissions; IWDW smoke reports; ancillary data; QA summaries
| IWDW→Ramboll |  |  | Unmerged model ready anthro. emissions from UNC
|  |  | AS | 2014v2 fires
| AS→IWDW→Ramboll |  |  | Modeled Fires
|  |  | Ramboll | Processing of modeled fires
| UNC→IWDW→ Ramboll |  |  | Unmerged gridded anthro. emissions
|  |  | Ramboll | Combine UNC anthro. emissions, AS fire emissions, and Ramboll natural emsisions; generate merged CAMx/CMAQ model ready emissions on 36/12km domains
| Ramboll→IWDW |  |  | Complete set of emissions inputs, ancillary data (spatial surrogates, speciation profiles) model ready emissions; QA summaries
PGM |  |  | Ramboll |  | Set up CAMx/CMAQ 36km NA, 12km CONUS for 2014
|  |  | Ramboll |  | WAQS vs EPA WRF sensitivity
|  |  | Ramboll |  | MEGAN vs. BEIS sensitivity
|  |  | Ramboll |  | AQ modeling sensitivity; how does modeling affect pockets of NAAs in western states, etc.
|  |  | Ramboll |  | 2014 annual CAMx and CMAQ 36/12km simulations using preferred configuration
|  |  | Ramboll |  | Generate MPE products using AMET | Specify other MPE analysis tools, scope of MPE products
| Ramboll→IWDW |  |  | O3 column, chem, tuv, landuse, ocean (CMAQ) | Transfer “other” inputs required for PGM modeling
| Ramboll→IWDW |  |  | PGM output | CAMx/CMAQ 3D conc., deposition output
| Ramboll→IWDW |  |  | MPE products | AMET scripts, MySQL db, AQOBS | Other MPE products? | Spring, 2019
|  |  | IWDW | MET, PGM output | MPE using AMET and other tools