## Slide 1: Overview of WRAP 2014 Platform develop and Shake-Out project update
Ralph Morris, Tejas Shah, Marco Rodriguez, Jeremiah Johnson, Pradeepa Vennam, Kaity Lieschke, Ramboll
B.H. Baek, UNC
January 31, 2019

## Slide 2: WRAP 2014 Shake-Out Objectives
Use existing information to develop a 2014 PGM modeling platform for western U.S. and provide initial testing
  3-month project
  EPA 2014 Platform (12US2)
  2014 WRF
    EPA (12US2) & WAQS (36US/12WUS2)
  SMOKE 36-km Domain
  New Natural Emissions
  Sensitivity Tests for WRF 12-km met and Biogenic
  2014 CAMx and CMAQ 36/12-km Annual Shake-Out Runs
    Evaluate fire plume rise

## Slide 3: 2014 Shake-Out Tasks
Task 1: Modeling Plan
  Draft Modeling Plan for 2014 Shake-Out dated December 31, 2018
  Two comments received – Any more?
  To do Modeling Plan on Lessons Learned (e.g., 2008 WestJumpAQMS and 2011 WAQS)
No Task 2
Task 3: 2014 Base Year Emissions Process
Task 4: 2014 WRF Meteorology MPE (PPT)
Task 5: 2014 GEOS-Chem BCs (PPT)
Task 6: 2014 PGM Modeling (contract update received Jan 29, 2019; Update Slide to Follow)
Task 7: Single-Source Visibility Modeling
No Tasks 8, 9 and 10
Task 11: Data Transfer to IWDW
Task 12: Management

## Slide 4: Task 1: Modeling Plan
Draft 2014 Platform Development and Shake-Out Modeling Plan dated December 31, 2018
  Asked for comments by January 22, 2019
  Received four comments
Update Draft 2014 Modeling Plan to address comments and redistribute by February 4, 2019
  Would like comments by end of week (February 8, 2019)
Second “Modeling Plan” on lessons learned from 2008/2011 and preliminary 2014 modeling that can be accounted for in 2014v2 Platform Update
  Draft by end of Feb 2019

## Slide 5: Task 3: 2014 Emissions Processing
Start with EPA’s 2014 Modeling CMAQ-ready emissions for 12-km 12US2 modeling domains
2014 Anthropogenic Emissions (UNC Lead)
  SMOKE Processing for 36-km 36US1 Domain
  SMOKE Processing of 2014 Point and Non-Point with western state updates:
    Point: O&G, EGU, nonEGU
    Non-Point: RWC, FugDust, Other (Area)
  Transfer of 2014 36/12-km CMAQ-ready sector emissions to Ramboll (Jan 30, 2019)
    CMAQ2CAMx convertor
2014 Natural Emissions
  MEGANv3 Biogenic (compare with EPA SMOKE-BEIS)
  Sea Salt processor (SSA/DMS) – CAMx with DMS chemistry not ready, rename DMS as SO2
  New WBD Processor – Needs more refinement
  New 2014 Fires from Air Sciences (received January 30, 2019)

## Slide 6: Task 4: 2014 WRF Model Evaluation (PPT to Follow)
Two WRF 12-km Datasets:
  EPA 12-km 12US2 and WAQS 12-km WUS2
Quantitative Evaluation using Surface Met
  Wind Speed, Wind Direction, Temperature and Humidity
  Evaluate for WUS, by State and by Site (make available on IWDW)
Qualitative Evaluation of Precipitation using PRISM Data
  Monthly and Daily Evaluation

## Slide 7: Task 5: 2014 GEOS-Chem Boundary Conditions (PPT to follow)
Process 2014 GEOS-Chem to generate BCs for CAMx and CMAQ 25-layer 36US domain
  Update species mapping in GC2CAMx and GC2CMAQ
Conduct inert with deposition BC-only CAMx 36-km 36US1 and 12-km 12US2 domains simulations and analyze spatial plots and evaluation against CASTNet O3 and IMPROVE
  As just simulating BCs (no emissions or chemistry) would expect model to underestimate
  Potential issues seen with Ozone, Crustal (Fine and Coarse) and SO4
  No issues seen with NH3 and NaCl that have been seen in past Global runs
Adjust 2014 BCs to eliminate anomalies
  Use capping of maximum species to eliminate anomalies (Ozone, SO4 and SO2)
  Don’t use scaling that should be addressed with GEOS-Chem emission updates
Rerun inert BC-only CAMx 36-km simulation
  Analyze Results

## Slide 8: Task 6: 2014 PGM Modeling
CAMx and CMAQ 2014 Annual Shake-Out Runs
Subtask 6a: PGM Set-Up and Initial Sensitivity Modeling
  WRF 12-km Sensitivity (EPA 12US2 vs. WAQS 12 WUS1)
  Biogenic Sensitivity (MEGAN vs. BEIS)
  Select configuration for 2014 Shake-Out Runs
Subtask 6b: Annual 2014 CAMx and CMAQ 36/12-km Shake-Out Runs
  Model Performance Evaluation
  Lessons Learned / Recommendations for Next Steps
  Additional Sensitivity Tests:
    Fire Plume Rise (EPA Briggs vs. WRAP Approach)
    [No Layer Collapsing]

## Slide 9: Tasks 7 (Single-Source) 11 (Transfer) and 12 (Management)
Task 7: Single-Source Visibility Screening and Modeling
  Preparation of PPT and Conduct Webinar December 12, 2018
  Document in Memorandum – Is this needed? Is there interest by states?
    Separate Q/D Analysis Project for Control Measures Subcommittee
Task 11: Data Transfer to IWDW
  Major transfers to occur in February
Task 12: Management
  Meetings, Conference Calls, Coordination, Progress Reports
  WRAP 2014 Shake-Out Meeting March 7, 2019 in Greater Denver Area

## Slide 10: Revised milestone schedule
Highlighted are completed work elements